## Sheet1
Progress log
Date | Description | Date completed | Comments
2021-02-26 | Ideas for the drawing app discussedd | 2021-02-26 | Edit Shape tool, eraser tool, load image button, pencil/line width tool
2021-02-26 | Started the development of edit shape tool | 2021-03-19 | finished tool to a certain extent however with a few bugs and doesn’t have an options button.
2021-03-12 | Started the developmentof eraser tool | 2021-03-19 | Finished the tool but works when mouse is clicked
2021-03-12 | README File for the application | 2021-03-19 | Added the file to the app as a textfile to read what the app is and the developments that have been added
2021-03-19 | submitting for peer-review | 2021-03-19 | submitted my file before 4pm
2021-03-19 | Peer-review feedback | 2021-03-26 | looked at all the applications given to me and made notable feedback
2021-03-26 | star trail tool | 2021-04-09 | star trail impelmented and tested
2021-04-09 | pencil/line width adjustment | 2021-04-23 | pencil/line tool adjusted to make sure that it doesnt affect other tools like star tril or edit shape tool
2021-04-19 | Final Adjustments and sorting any new bugs | 2021-04-25 | Sorted any issues, fixed the indentation and made a note of any changes in the testing logs.